## Cover Sheet
Pilot 2
Project Name <<>>
Requirements Traceability Matrix
Version: <1.0>
Document Purpose: This document is a combined requirements gathering document and Requirements Traceability Matrix (RTM). It is used to document high level requirements, detailed product requirements and full traceability of these requirements through the software lifecycle. This template is part of the High Definition Lifecycle. This document is a living document and should be maintained for the duration of the project.

## High-level Requirements
High-level Requirements
Project Name: | New Codington Project Online / FERS
Project Stage: | Plan
High-level Requirement ID | Business Topic | Requirement Name | Short Description | Priority | Release Number | Description | Requirement Source | Business/ Process Area | Stability | Dependencies | Status | Owner | Change Request ID | Is this an Interface Requirement? (Y/N) | Notes
Requirements and Traceability | Application Functionality |  |  | High | 1 |  | SOW | Public Relations | High | None | Approved | Michael Stevens | N/A | N | None
BREQ 2.0.0 | Application Functionality |  |  | High | 1 |  | SOW | Public Relations | High | BREQ 1.0.0 | Approved | Michael Stevens | N/A | N | None
BREQ 3.0.0 | Application Functionality |  |  | High | 1 |  | SOW | Public Relations | High | BREQ 2.0.0 | Approved | Michael Stevens | N/A | N | None
BREQ 4.0.0 | Application Functionality |  |  | High | 1 |  | SOW | Public Relations | High | BREQ 2.0.0 | Approved | Michael Stevens | N/A | N | None
BREQ 5.0.0 | Application Functionality |  |  | High | 1 |  | SOW | Public Relations | High | BREQ 4.0.0 | Approved | Michael Stevens | N/A | N | None
END OF FERS RELEASE 1 HIGH LEVEL REQUIREMENTS
Please don't Change below this line
Status
Approved
Rejected
Deferred
In-Progress
Note on E6: This column is linked with the Priority column on RTM - Lifecycle Tracking worksheet. The RTM - Lifecycle Tracking worksheet will pre-populate with the Priority column when it is entered here. High - Critical, can't live without Medium - Important-not critical but strongly desired by stakeholders Low - Optional, nice to have
Note on J6: The stability of the requirement (i.e. how likely it is for the requirement to change. High stability = low likelihood of change.)
Note on K6: Requirement IDs of all the requirements (both functional and non-functional) on which this requirement has a dependency.

## Product Requirements
Product Requirements
Project Name: | New Codington Project Online / FERS
Project Stage: | Analyse
Requirement ID | Business Topic | Requirement Name | Short Description | Requirement Type | Requirement Sub Type | Priority | Release Number | Long Description | Requirement Source | Business/ Process Area | Stability | Dependencies | Status | Owner | Change Request ID | Notes
BREQ 1.1.0 | Application Functionality |  |  | Application | Functional | High | 1 |  | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | None | Approved | NCCC | N/A | None
BREQ 1.1.1 | Application Functionality |  |  | Application | Functional | High | 1 |  | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | None | Approved | NCCC | N/A | None
BREQ 1.1.2 | Application Functionality |  |  | Application | Functional | High | 1 |  | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | None | Approved | NCCC | N/A | None
BREQ 1.2.0 | Application Functionality |  |  | Application | Functional | High | 1 |  | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | None | Approved | NCCC | N/A | None
BREQ 1.2.1 | Application Functionality |  |  | Application | Functional | High | 1 |  | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | None | Approved | NCCC | N/A | None
BREQ 1.2.2 | Application Functionality |  |  | Application | Functional | High | 1 |  | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | None | Approved | NCCC | N/A | None
BREQ 1.2.3 | Application Functionality |  |  | Application | Security and Control | High | 1 |  | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | None | Approved | NCCC | N/A | None
BREQ 1.3.0 | Application Functionality |  |  | Application | Functional | High | 1 |  | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | BREQ 2.0.0 | Approved | NCCC | N/A | None
BREQ 1.3.1 | Application Functionality |  |  | Application | Functional | High | 1 |  | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | BREQ 2.0.0 | Approved | NCCC | N/A | None
BREQ 1.3.2 | Application Functionality |  |  | Application | Functional | High | 1 |  | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | None | Approved | NCCC | N/A | None
BREQ 1.3.3 | Application Functionality |  |  | Application | Functional | High | 1 |  | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | None | Approved | NCCC | N/A | None
BREQ 1.3.4 | Application Functionality |  |  | Application | Functional | High | 1 |  | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | None | Approved | NCCC | N/A | None
BREQ 1.3.5 | Application Functionality |  |  | Application | Functional | High | 1 |  | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | None | Approved | NCCC | N/A | None
BREQ 1.3.6 | Application Functionality |  |  | Application | Functional | High | 1 |  | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | None | Approved | NCCC | N/A | None
BREQ 1.3.7 | Application Functionality |  |  | Application | Functional | High | 1 |  | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | None | Approved | NCCC | N/A | None
BREQ 1.3.8 | Application Functionality |  |  | Application | Functional | High | 1 |  | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | None | Approved | NCCC | N/A | None
BREQ 1.3.9 | Application Functionality |  |  | Application | Functional | High | 1 |  | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | None | Approved | NCCC | N/A | None
BREQ 1.3.10 | Application Functionality |  |  | Application | Functional | High | 1 |  | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | None | Approved | NCCC | N/A | None
BREQ 2.0.1 | Application Functionality |  |  | Application | Security and Control | High | 1 |  | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | BREQ 2.0.0 | Approved | NCCC | N/A | None
BREQ 2.0.2 | Application Functionality |  |  | Application | Security and Control | High | 1 |  | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | BREQ 2.0.0 | Approved | NCCC | N/A | None
BREQ 3.1.0 | Application Functionality |  |  | Application | Content | High | 1 |  | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | BREQ 2.0.0 | Approved | NCCC | N/A | None
BREQ 3.1.1 | Application Functionality |  |  | Application | Functional | High | 1 |  | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | BREQ 2.0.0 | Approved | NCCC | N/A | None
BREQ 3.1.2 | Application Functionality |  |  | Application | Functional | High | 1 |  | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | BREQ 2.0.0 | Approved | NCCC | N/A | None
BREQ 3.1.3 | Application Functionality |  |  | Application | Functional | High | 1 |  | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | BREQ 2.0.0 | Approved | NCCC | N/A | None
BREQ 3.1.4 | Application Functionality |  |  | Application | Functional | High | 1 |  | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | BREQ 2.0.0 | Approved | NCCC | N/A | None
BREQ 3.1.5 | Application Functionality |  |  | Application | Functional | High | 1 |  | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | BREQ 2.0.0 | Approved | NCCC | N/A | None
BREQ 3.1.6 | Application Functionality |  |  | Application | Functional | High | 1 |  | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | BREQ 2.0.0 | Approved | NCCC | N/A | None
BREQ 3.1.7 | Application Functionality |  |  | Application | Functional | High | 1 |  | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | BREQ 2.0.0 | Approved | NCCC | N/A | None
BREQ 3.2.0 | Application Functionality |  |  | Application | Functional | High | 1 |  | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | BREQ 2.0.0 | Approved | NCCC | N/A | None
BREQ 3.2.1 | Application Functionality |  |  | Application | Functional | High | 1 |  | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | BREQ 2.0.0 | Approved | NCCC | N/A | None
BREQ 3.2.2 | Application Functionality |  |  | Application | Functional | High | 1 |  | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | BREQ 2.0.0 | Approved | NCCC | N/A | None
BREQ 3.3.0 | Application Functionality |  |  | Application | Functional | High | 1 |  | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | BREQ 2.0.0 | Approved | NCCC | N/A | None
BREQ 3.3.1 | Application Functionality |  |  | Application | Functional | High | 1 |  | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | BREQ 3.0.0 | Approved | NCCC | N/A | None
BREQ 3.3.2 | Application Functionality |  |  | Application | Functional | High | 1 |  | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | BREQ 4.0.0 | Approved | NCCC | N/A | None
BREQ 3.3.3 | Application Functionality |  |  | Application | Functional | High | 1 |  | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | BREQ 5.0.0 | Approved | NCCC | N/A | None
BREQ 3.3.4 | Application Functionality |  |  | Application | Functional | High | 1 |  | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | BREQ 2.0.0 | Approved | NCCC | N/A | None
BREQ 3.3.5 | Application Functionality |  |  | Application | Functional | High | 1 |  | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | BREQ 2.0.0 | Approved | NCCC | N/A | None
BREQ 3.3.6 | Application Functionality |  |  | Application | Functional | High | 1 |  | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | BREQ 2.0.0 | Approved | NCCC | N/A | None
BREQ 3.3.7 | Application Functionality |  |  | Application | Functional | High | 1 |  | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | BREQ 2.0.0 | Approved | NCCC | N/A | None
BREQ 3.3.8 | Application Functionality |  |  | Application | Functional | High | 1 |  | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | BREQ 2.0.0 | Approved | NCCC | N/A | None
BREQ 3.3.9 | Application Functionality |  |  | Application | Functional | High | 1 |  | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | BREQ 2.0.0 | Approved | NCCC | N/A | None
BREQ 4.0.1 | Application Functionality |  |  | Application | Functional | High | 1 |  | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | BREQ 2.0.0 | Approved | NCCC | N/A | None
BREQ 4.0.2 | Application Functionality |  |  | Application | Functional | High | 1 |  | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | BREQ 2.0.0 | Approved | NCCC | N/A | None
BREQ 5.0.1 | Application Functionality |  |  | Application | Functional | High | 1 |  | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | BREQ 4.0.0 | Approved | NCCC | N/A | None
END OF RELEASE 1 PRODUCT REQUIREMENTS
Please Don't Change below the Line
Application
Deployment
Support
Technical
Training & Performance Spt
Sub-Types
Functional
Quality
Interface/Data
Security and Control
Content
Development Environment
Execution Environment
Operations Environment
Status
Proposed
Approved
Incorporated
Validated
Release
1
2
3
4
5
Priority
High
Medium
Low
Note on A7: This column is linked with the Requirements ID column on the RTM - Lifecycle Tracking worksheet. The RTM - Lifecycle Tracking sheet will pre-populate with the Requirement ID when it is entered here.
Note on D7: This column is linked with the Short Description column on RTM - Lifecycle Tracking worksheet. The RTM - Lifecycle Tracking worksheet will pre-populate with the Short Description column when it is entered here.
Note on F7: Only applicable for Application and Technical Requirements
Note on G7: This column is linked with the Priority column on RTM - Lifecycle Tracking worksheet. The RTM - Lifecycle Tracking worksheet will pre-populate with the Priority column when it is entered here. High - Critical, can't live without Medium - Important-not critical but strongly desired by stakeholders Low - Optional, nice to have
Note on H7: This column is linked with the Release Number column on RTM - Lifecycle Tracking worksheet. The RTM - Lifecycle Tracking sheet will pre-populate with the Release Number when it is entered here.
Note on L7: The stability of the requirement (i.e. how likely it is for the requirement to change. High stability = low likelihood of change.)
Note on M7: Requirement IDs of all the requirements (both functional and non-functional) on which this requirement has a dependency.

## RTM - Lifecycle Tracking
Requirements Traceability Matrix
NOTE: The Requirement ID, Short Description, Release Number and Priority columns are linked with the Requirements ID field on the Product Requirements worksheet. These field will pre-populate by the respective column on the Product Requirements worksheet.
Project Stage: | Analyse
Product Requirements |  |  |  |  | Analyze Stage | [8 empty] | Design Stage | [14 empty] | Build Stage
[5 empty] | Application |  |  |  | Technical Architecture |  |  |  |  | Application | [6 empty] | Technical Architecture |  |  |  |  | Test |  |  | Application |  |  |  | Test
Requirement ID | Short Description | Release Number | Priority (H, M, L) | High-level Requirement ID or SOW Reference | Use Case Diagram and User Scenarios | Use Case | Report and Batch Process Descriptions | System Integration Flow | Application Architecture Specification | Development Architecture Specification | Execution Architecture Specification | Operations Architecture Specification | Infrastructure Architecture Specification | System Integration Design | Component/ Class Design (CCD) | Report Design | Page Specification | Database Conversion Design | Physical Database Design | Assembly Test Conditions and Scenarios | Application Architecture Component Design | Development Architecture Component Design | Execution Architecture Component Design | Operations Architecture Component Design | Infrastructure Architecture Design | Application Product Test Conditions and Scenarios | Integration Product Test Conditions and Scenarios | Performance Test Conditions and Scenarios | Source Code Modules | Unit Test Conditions and Scenarios | Assembly Test Script | Unit Test Script | Application Product Test Script | Integration Product Test Script | Performance Test Script
BREQ 1.1.0 |  | 1 | High | None | PROJ_SC_1 | registerNewUser | Not Available | Not Available | Optional Reference available (Draft version) | Refer to the Development Architecture Specification Presentation for details | Not Available | Not Available | Refer to the Infrastructure Architecture Specification Presentation for details | Not Available | Refer to the CCD documents available with references to the Javadocs | Not Available | Not Available. Refer to the Wireframes for details. | Not Available | Refer to the Physical Database Document | Refer to the Test documents | Out -of scope for this project release | Out -of scope for this project release | Out -of scope for this project release | Out -of scope for this project release | Out -of scope for this project release | Refer to the Test documents | Out -of scope for this project release | Out -of scope for this project release | Refer to the Actual code | Refer to Unit Test conditions and Scenarios document Note that the traceability back to requirements wont be available completely in the above mentioned reference | Refer to Test documents & relevant test cycle control sheet for details | Refer to Test documents & relevant test cycle control sheet for details | Refer to the Test documents | Out -of scope for this project release | Out -of scope for this project release
BREQ 1.1.1 |  | 1 | High | None | PROJ_SC_1 | registerNewUser
BREQ 1.1.2 |  | 1 | High | None | PROJ_SC_1 | registerNewUser
BREQ 1.2.0 |  | 1 | High | Requirements and Traceability | PROJ_SC_1 | registerNewUser
BREQ 1.2.1 |  | 1 | High | Requirements and Traceability | PROJ_SC_1 | registerNewUser
BREQ 1.2.2 |  | 1 | High | Requirements and Traceability | PROJ_SC_1 | registerNewUser
BREQ 1.2.3 |  | 1 | High | Requirements and Traceability | PROJ_SC_1 | registerNewUser
BREQ 1.3.0 |  | 1 | High | Requirements and Traceability | PROJ_SC_1 | registerNewUser
BREQ 1.3.1 |  | 1 | High | Requirements and Traceability | PROJ_SC_1 | registerNewUser
BREQ 1.3.2 |  | 1 | High | Requirements and Traceability | PROJ_SC_1 | registerNewUser
BREQ 1.3.3 |  | 1 | High | Requirements and Traceability | PROJ_SC_1 | registerNewUser
BREQ 1.3.4 |  | 1 | High | Requirements and Traceability | PROJ_SC_1 | registerNewUser
BREQ 1.3.5 |  | 1 | High | Requirements and Traceability | PROJ_SC_1 | registerNewUser
BREQ 1.3.6 |  | 1 | High | Requirements and Traceability | PROJ_SC_1 | registerNewUser
BREQ 1.3.7 |  | 1 | High | Requirements and Traceability | PROJ_SC_1 | registerNewUser
BREQ 1.3.8 |  | 1 | High | Requirements and Traceability | PROJ_SC_1 | registerNewUser
BREQ 1.3.9 |  | 1 | High | Requirements and Traceability | PROJ_SC_1 | registerNewUser
BREQ 1.3.10 |  | 1 | High | Requirements and Traceability | PROJ_SC_1 | registerNewUser
BREQ 2.0.1 |  | 1 | High | BREQ 2.0.0 | PROJ_SC_1 | loginUser
BREQ 2.0.2 |  | 1 | High | BREQ 2.0.0 | PROJ_SC_1 | loginUser
BREQ 3.1.0 |  | 1 | High | BREQ 3.0.0 | PROJ_SC_1 | updateUserInfo
BREQ 3.1.1 |  | 1 | High | BREQ 3.0.0 | PROJ_SC_1 | updateUserInfo
BREQ 3.1.2 |  | 1 | High | BREQ 3.0.0 | PROJ_SC_1 | updateUserInfo
BREQ 3.1.3 |  | 1 | High | BREQ 3.0.0 | PROJ_SC_1 | updateUserInfo
BREQ 3.1.4 |  | 1 | High | BREQ 3.0.0 | PROJ_SC_1 | updateUserInfo
BREQ 3.1.5 |  | 1 | High | BREQ 3.0.0 | PROJ_SC_1 | updateUserInfo
BREQ 3.1.6 |  | 1 | High | BREQ 3.0.0 | PROJ_SC_1 | updateUserInfo
BREQ 3.1.7 |  | 1 | High | BREQ 3.0.0 | PROJ_SC_1 | updateUserInfo
BREQ 3.2.0 |  | 1 | High | BREQ 3.0.0 | PROJ_SC_1 | updateUserInfo
BREQ 3.2.1 |  | 1 | High | BREQ 3.0.0 | PROJ_SC_1 | updateUserInfo
BREQ 3.2.2 |  | 1 | High | BREQ 3.0.0 | PROJ_SC_1 | updateUserInfo
BREQ 3.3.0 |  | 1 | High | BREQ 3.0.0 | PROJ_SC_1 | updateUserInfo
BREQ 3.3.1 |  | 1 | High | BREQ 3.0.0 | PROJ_SC_1 | updateUserInfo
BREQ 3.3.2 |  | 1 | High | BREQ 3.0.0 | PROJ_SC_1 | updateUserInfo
BREQ 3.3.3 |  | 1 | High | BREQ 3.0.0 | PROJ_SC_1 | updateUserInfo
BREQ 3.3.4 |  | 1 | High | BREQ 3.0.0 | PROJ_SC_1 | updateUserInfo
BREQ 3.3.5 |  | 1 | High | BREQ 3.0.0 | PROJ_SC_1 | updateUserInfo
BREQ 3.3.6 |  | 1 | High | BREQ 3.0.0 | PROJ_SC_1 | updateUserInfo
BREQ 3.3.7 |  | 1 | High | BREQ 3.0.0 | PROJ_SC_1 | updateUserInfo
BREQ 3.3.8 |  | 1 | High | BREQ 3.0.0 | PROJ_SC_1 | updateUserInfo
BREQ 3.3.9 |  | 1 | High | BREQ 3.0.0 | PROJ_SC_1 | updateUserInfo
BREQ 4.0.1 |  | 1 | High | BREQ 4.0.0 | PROJ_SC_1 | updateUserInfo
BREQ 4.0.2 |  | 1 | High | BREQ 4.0.0 | PROJ_SC_1 | registerForNewEvent
BREQ 5.0.1 |  | 1 | High | BREQ 5.0.0 | PROJ_SC_1 | unregisterFromExistingEvent
Note on A7: This column is linked with the Requirements ID field on the Product Requirements worksheet. This field will be pre-populated by the Requirements ID column on the Product Requirements worksheet. There is no need to enter the Requirements ID twice.
Note on B7: This column is linked to Short Description column on Product Requirements worksheet. This field will be pre-populated by the Short Description column on the Product Requirements worksheet. There is no need to enter the Short Description twice.
Note on C7: This column is linked to Release Number column on Product Requirements worksheet. This field will be pre-populated by the Release Number column on the Product Requirements worksheet. There is no need to enter the Release Number twice.
Note on D7: This column is linked to Priority column on Product Requirements worksheet. This field will be pre-populated by the Priority column on the Product Requirements worksheet. There is no need to enter the Priority twice.
Note on E7: Enter the ID of the corresponding high-level requirement. If such a high-level requirement does not exist, put in the reference to the Statement of Work.
Note on AG7: Note: For 'Unit Test' the script will be written in code implementing the test conditions for the scenario being coded, as opposed to the standard test script template.

## Assumptions
Assumptions
Project Stage: | Analyse
Assumption ID | Assumption | Stage | Status | Requirement ID | Date
ASID_001 |  | Plan | Valid | PR_002.10 | 2012-02-27
ASID_002 |  | Plan | Valid | PR_0002.4 | 2012-02-27
ASID_003 |  | Plan | Valid | None | 2012-03-12
ASID_004 |  | Plan | Valid | None | 2012-03-12
ASID_003 |  | Plan | Valid | None | 2012-03-12
ASID_003 |  | Plan | Valid | None | 2012-03-12
Please do not change below this line
Stage
Plan
Analyse
Design
Build
Test
Deploy
Note on C4: Enter the stage of the project when the assumption was made.
Note on D4: Indicate in this cell if the assumption is still valid or if it has been invalidated by a new requirement.
Note on E4: When an assumption has been invalidated by a new requirement, track the requirement ID(s) in this column.
Note on F4: Insert the date the assumption was made, and update if it is invalidated.